## Tickets
Ticket | Epic | What it delivers | Model to fire | Status | Merged | Contract
E11-T1 | E11 split payments | Split-payment math in the domain (partition preview, labeled portions) | Opus | Merged | 2026-08-20 | docs/tickets/E11-T1-split-domain.md
E11-T2 | E11 split payments | Split commands and API on the engine | Opus | Merged | 2026-08-20 | docs/tickets/E11-T2-split-engine.md
E11-T3 | E11 split payments | Split payments on the POS page (full / even / by seat) | Sonnet | Merged | 2026-08-22 | docs/tickets/E11-T3-split-pos-ui.md
E8-T2 | E8 kitchen | Guardrail against KDS/check state drift | Opus | Merged | 2026-08-22 | docs/tickets/E8-T2-kds-drift.md
E11-T4 | E11 split payments | Cross-partition guard (no double-settling a line) | Opus | Merged | 2026-08-22 | docs/tickets/E11-T4-cross-partition-guard.md
E19-T1 | E19 reports | Insights read APIs: server scorecard + sales heatmap, computed on read | Opus | Merged | 2026-08-23 | docs/tickets/E19-T1-insights-core.md
E19-T2 | E19 reports | The Reports page: tiles, scorecard, heatmap | Sonnet | Merged | 2026-08-23 | docs/tickets/E19-T2-insights-page.md
E19-T3 | E19 reports | Declared-tips total wired to the real source | Opus | Merged | 2026-08-23 | docs/tickets/E19-T3-declared-tips.md
E20-T1 | E20 guestbook | Guestbook specification (identity ladder, privacy defaults) | Sonnet | Merged | 2026-08-23 | docs/tickets/E20-T1-guestbook-spec.md
E20-T2 | E20 guestbook | Guestbook engine: guests, attach, merge, derived profile | Opus | Merged | 2026-08-23 | docs/tickets/E20-T2-guestbook-core.md
E19-T4 | E19 reports | Insights renamed to Reports everywhere (D24) | Sonnet | Merged | 2026-08-23 | docs/tickets/E19-T4-rename-reports.md
E20-T3 | E20 guestbook | Guest screens: search, profile, attach from the check | Sonnet | Merged | 2026-08-23 | docs/tickets/E20-T3-guestbook-screens.md
E2-T2 | E2 state machines | Reopened check can always close out (liveness fix) | Opus | Merged | 2026-08-23 | docs/tickets/E2-T2-reopen-closeout.md
E8-T3 | E8 kitchen | Per-course hold/fire on the check + check history read | Opus | Merged | 2026-08-24 | docs/tickets/E8-T3-course-hold-fire.md
UI-T1 | UI parity (D25) | Left icon rail app shell on every screen | Sonnet | Merged | 2026-08-24 | docs/tickets/UI-T1-app-shell.md
UI-T2 | UI parity (D25) | Menu category rail on Service | Sonnet | Merged | 2026-08-24 | docs/tickets/UI-T2-menu-category-rail.md
UI-T3 | UI parity (D25) | Check panel: course controls, action bar, batch void, history | Sonnet | Merged | 2026-08-25 | docs/tickets/UI-T3-check-panel.md
UI-T4 | UI parity (D25) | New-check modal knows seats, areas, and party size | Sonnet | Merged | 2026-08-25 | docs/tickets/UI-T4-new-check-capacity.md
E6-T2 | E6 floor | Floor editor engine: add / edit / resize / retire (soft), revive | Opus | Merged | 2026-08-27 | docs/tickets/E6-T2-floor-editor-core.md
E21-T1 | E21 venue | Venue settings + staff management engine (hashed PINs, last-manager guard) | Opus | Merged | 2026-08-27 | docs/tickets/E21-T1-venue-staff-core.md
E6-T3 | E6 floor | Floor editor UI: shapes, areas, retire with confirm | Sonnet | Merged | 2026-08-28 | docs/tickets/E6-T3-floor-editor-ui.md
E21-T2 | E21 venue | Settings screen + venue name on every header, receipt, lock screen | Sonnet | Merged | 2026-08-28 | docs/tickets/E21-T2-settings-screen.md
E22-T1 | E22 migration | Migration specification (what moves, what never does) | Sonnet | Merged | 2026-08-28 | docs/tickets/E22-T1-migration-spec.md
E23-T1 | E23 reservations | Reservations specification (promise, not a lock) | Sonnet | Merged | 2026-08-28 | docs/tickets/E23-T1-reservations-spec.md
E24-T1 | E24 team & labor | Team & labor specification (the three-rung ladder) | Sonnet | Merged | 2026-08-28 | docs/tickets/E24-T1-team-labor-spec.md
E24-T2 | E24 team & labor | People directory: titles, PIN-gated contact details | Opus | Merged | 2026-09-01 | docs/tickets/E24-T2-people-directory.md
E5-T2 | E5 menu | Modifier groups editable end to end on the draft | Opus | Merged | 2026-09-01 | docs/tickets/E5-T2-menu-groups-core.md
E24-T3 | E24 team & labor | Payroll hours + tips CSV export (never computes pay) | Opus | Merged | 2026-09-01 | docs/tickets/E24-T3-hours-export.md
E5-T3 | E5 menu | Modifier groups on the Menu screen | Sonnet / Codex | Merged | 2026-09-01 | docs/tickets/E5-T3-menu-groups-ui.md
E22-T2 | E22 migration | Menu CSV import: idempotent draft, per-row report, Nine Thai fixture | Opus | Merged | 2026-09-02 | docs/tickets/E22-T2-menu-import-core.md
E22-T3 | E22 migration | Import action on the Menu screen (file, paste, template, report) | Sonnet / Codex | Merged | 2026-09-02 | docs/tickets/E22-T3-menu-import-ui.md
E23-T2 | E23 reservations | Call-in book engine: book, seat in one command, floor badge | Opus | Merged | 2026-09-02 | docs/tickets/E23-T2-reservations-core.md
E23-T3 | E23 reservations | Reservations screen + floor badges, phone-first | Sonnet / Codex | Merged | 2026-09-03 | docs/tickets/E23-T3-reservations-ui.md
E21-T3 | E21 venue | Timezone picker shows itself on focus | Sonnet / Codex | Merged | 2026-09-03 | docs/tickets/E21-T3-timezone-picker-polish.md
E24-T4 | E24 team & labor | Scheduling engine: planned shifts, publish gate, planned vs actual hours | Opus | Merged | 2026-09-03 | docs/tickets/E24-T4-scheduling-core.md
E24-T5 | E24 team & labor | Schedule screen: My week, Plan grid, Hours | Sonnet / Codex | Merged | 2026-09-03 | docs/tickets/E24-T5-scheduling-ui.md
E26-T1 | E26 inventory | Inventory specification (recipes, derived depletion, the 86 bridge) | Sonnet / Codex | Merged | 2026-09-03 | docs/tickets/E26-T1-inventory-spec.md
E25-T1 | E25 roles | Roles engine: owner / manager / kitchen / server, matrix enforced server-side | Opus | Merged | 2026-09-03 | docs/tickets/E25-T1-roles-core.md
E25-T2 | E25 roles | Every page's rail obeys the signed-in role; calm refusal page; reads send x-device-id | Sonnet / Codex | Merged | 2026-09-04 | docs/tickets/E25-T2-roles-ui.md
UI-T5 | App shell (D35) | Back-office card hub at /office; floor keeps the rail; land by role | Sonnet / Codex | Merged | 2026-09-04 | docs/tickets/UI-T5-back-office-hub.md
E26-T2 | E26 inventory | Inventory engine: ingredients, recipe links, counts, receipts, 86 proposals | Opus | Planned (gated on Andy's spec review) |  | written after the spec review
E26-T3 | E26 inventory | Chef's screens: what is low, order list, count sheet | Sonnet / Codex | Planned (gated on Andy's spec review) |  | written after the spec review

## Parked and gated
Work | Waits on | Decision
Vendor-format import converters (Toast / Square / NorthStar) | A real customer EXPORT file in hand (the NorthStar sheet is a load template, not an export) | D30
Guest list import | Matt's consent deck (deck C/D answers on guest data) | D30
Staff CSV import | A real roster worth batching (a hire is five seconds) | D30
Address autocomplete in Settings | Third-party by nature (Google Places / Mapbox); needs an online-integrations ADR | D32
Online booking (OpenTable / Resy) | Integrate, never build; deck E tells us which platform, if any | D27
Reservation deposits / card holds | E13 payments + ADR-3 | D27
E13 payments integration | ADR-3 (Stripe vs Adyen), needs Matt | D2/D8
E9/E10 offline & LAN service | D6 (is LAN-continuous service P0?), needs Matt | D6
Decor elements on the floor editor | Post-D26 follow-up, founder call on priority | D26
Scheduling habits retrofit | Matt's deck F answers fold in via change control | D31
Prep items (sauces) in inventory | V2 per spec question G-3, after the founder's review | D34

## How to use
RestaurantOS ticket tracking log
Generated 2026-09-03 by the orchestrator; refreshed at every review pass. BACKLOG.md stays the source of truth for full detail.
To fire a ready ticket, open a worker session on the model in the 'Model to fire' column and paste:
You are a worker session. Execute the ticket at docs/tickets/<name>.md exactly; it is your entire scope.
Row colors on the Tickets sheet: green = merged, dark green = ready to fire now, amber = ready once its blocker merges, gray = gated on a decision or review.
Sonnet / Codex' means either works (D17); money, domain, and cross-module tickets stay Opus (D21).